## Ark 1
Lofthus Frukt og Saft |  | Start date | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | End date
|  | 2019-12-02 | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | 2020-01-01
Website Design |  | 23 | [20 empty] | Go live
Decide on elements to include in web design | Developer | 1
Plan general features and the layout of the pages | Developer | 2
Draw sketches of each page for desktop, tablet and mobile devices | Developer | 1
Create visual mockups in Illustrator for each page and size | Developer | 1
Propose design to the client | Developer | 1
Make alternative changes based on feedback | Developer | 3
Structure the HTML of the pages | Developer | 2
Settle on a color palette and a consistent use of colors throughout the project | Developer | 1
design the pages - mobile first - with CSS | Developer | 4
Present website to client | Developer | 1
Accessibility and WCAG optimalization | Developer | 5
User Experience testing | Developer
Cross browser and device testing | Developer
Present website to customer | Developer | 1 | [20 empty] | Launch Website
Photography |  | 20
Product photography | Photographer | 5
Images for visual elements and design, eg: page heros and banners | Photographer | 5
Create the graphics that will be consistent across marketing channels | Photographer | 10
Copywriting |  | 21
Create an identity and appearance for Lofthus | Copywriter | 5
Present content identity | Copywriter | 1
Provide copywriting for product descriptions and nutritional content | Copywriter | 5
Provide copywriting for website articles and paragraphs | Copywriter | 10
Marketing |  | 22
Market analysis | Marketer | 3
Marketing strategy | Marketer
Social media strategy | Marketer | 3
Present marketing campaign to customer | Marketer | 1
Branding | Marketer | 5
Search engine optimalization | Marketer | 5
Advertising | Marketer | 5 | [20 empty] | Drive traffic to website
Meetings |  | 5
Project kickoff meeting | Team + client | 2
Project status meeting | Team + client | 1
Stakeholder meeting | Team + client | 1
Project review and innovation meeting | Team + client | 1 | [20 empty] | Project review